## Release Plan (hidden)
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2006-06-13 | 42 | 2006-07-24 | 79
2 | 2006-07-25 | 42 | 2006-09-04 | 24
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2006-06-13 | 14 | 2006-06-26 | 28 | Planned |  | Planning | 1
2 | 2006-06-27 | 14 | 2006-07-10 | 26 | Planned |  | Specification and prototype development | 1
3 | 2006-07-11 | 14 | 2006-07-24 | 25 | Planned |  | Specification and prototype development | 1
4 | 2006-07-25 | 14 | 2006-08-07 | 24 | Planned |  | Specification and prototype development | 2
5 | 2006-08-08 | 14 | 2006-08-21 | 0 | Planned |  | Specification and prototype development, documentation | 2
6 | 2006-08-22 | 14 | 2006-09-04 | 0 | Planned |  | Usability test, documentation, prototype corrections | 2
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 103
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
EP222HT SCRUM
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | Html och grundläggande Css | Done | 2 | 1 |  | Javascript webapplikation
2 | Skapa formulär | Done | 12 | 1
3 | Funktion för att lägga till medlemmar | Done | 14 | 1 |  | Lägga till medlemmar i listan
4 | Funktion för att ta bort medlemmar | Done | 12 | 2 |  | Ta bort medlemmar ur listan
5 | Funktion för att automatisk tilldela ett unikt medlemsnummer till medlemmarna. | Done | 14 | 2 |  | Tilldelar unikt medlemsnummer.
6 | Ändra information på medlem. | Done | 15 | 3 |  | Kunna korrigera fel i registret
7 | Medlemsinformation | Done | 10 | 3 |  | Kunna se när medlemmen registrerades.
8 | Spara informationen | Ongoing | 14 | 4 |  | Spara medlemmarna i databas.
9 | Avslutande Css och stilning | Done | 10 | 4 |  | Försöka göra det vackert.
103
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 103 |  | Sprint count | 4
Count trend from last |  |  | 4 | sprints | Trend sprint count | 5
[5 empty] | Trend offset | 1 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 4 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 25.75 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
4 |  |  | 28.5 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 28.5 |  | Trend count | 6 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 28.5 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 26 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25.6 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 4
Original estimate - Max |  |  | 7 |  | Standard Dev. | 5.0662
4 |  |  | 4
Realized average |  |  | 3 |  | LastPlanned | 25
Average last 8 |  |  | 3 |  | LastRealized | 36
Avg. worst 3 in last 8 |  |  | 3
Trend |  |  | 5
Realized + St. Dev |  |  | 4
Realized - St. Dev |  |  | 4
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 103 | 28 | 26 | 103 | 103 | 103 | 0 | 0 | 103 | 102 | 102 | -11 | 28.5 | 28.5 | 26
2 | 77 | 26 | 27 | 103 | 77 | 77 | 0 | 0 | 77 | 76.4 | 76.4 | -11 | 28.5 | 28.5 | 26
3 | 50 | 25 | 25 | 103 | 50 | 50 | 0 | 0 | 50 | 50.8 | 50.8 | -11 | 28.5 | 28.5 | 26
4 | 25 | 24 | 36 | 103 | 25 | 25 | 0 | 0 | 25 | 25.2 | 25.2 | -11 | 28.5 | 28.5 | 26
5 |  |  |  |  | 0 | 0 | -11 | -11 | 0 | -0.4 | -0.4 | -11 | 28.5 | 28.5 | 26
6 | [9 empty] | -11 | -11 | -11 | 28.5 | 28.5 | 26
7 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
8 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
9 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
10 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
11 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
12 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
13 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
14 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
15 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
16 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
17 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
18 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
19 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
20 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
21 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
22 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
23 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
24 | [9 empty] | -11 |  | -11 | 28.5 | 28.5 | 26
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 28 | 28 | 24 | 15 | 3
Task rows | 3 | Done days | 4 |  | 28 | 22.4 | 16.8 | 11.2 | 5.6
Warning! These are necessary |  | Trend |  |  | 30.1 | 21.7 | 13.3 | 4.9
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 30.1 1: 1; 21.7 2: 2; 13.3 3: 3; 4.9 4: 4; 4.9 5: 5
Html och grundläggande CSS | 1 | Elof Paulsson | Done | 2 | 30.1 1: 2; 21.7 2: 0; 13.3 3: 0; 4.9 4: 0; 4.9 5: 0
Skapa formulär | 2 | Elof Paulsson | Done | 12 | 30.1 1: 12; 21.7 2: 10; 13.3 3: 5; 4.9 4: 0; 4.9 5: 0
Lägga till medlemmar | 3 | Elof Paulsson | Done | 14 | 30.1 1: 14; 21.7 2: 14; 13.3 3: 10; 4.9 4: 3; 4.9 5: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 26 | 26 | 14 | 5 | 2
Task rows | 2 | Done days | 4 |  | 26 | 20.8 | 15.6 | 10.4 | 5.2
Warning! These are necessary |  | Trend |  |  | 23.9 | 15.8 | 7.7
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 23.9 1: 1; 15.8 2: 2; 7.7 3: 3; 7.7 4: 4; 7.7 5: 5
Ta bort medlemmar. | 4 | Elof Paulsson | Done | 12 | 23.9 1: 12; 15.8 2: 4; 7.7 3: 0
Unikt medlemsnummer. | 5 | Elof Paulsson | Done | 14 | 23.9 1: 14; 15.8 2: 10; 7.7 3: 5; 7.7 4: 2; 7.7 5: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 25 | 25 | 11 | 2 | 2
Task rows | 2 | Done days | 4 |  | 25 | 20 | 15 | 10 | 5
Warning! These are necessary |  | Trend |  |  | 21.7 | 13.9 | 6.1
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 21.7 1: 1; 13.9 2: 2; 6.1 3: 3; 6.1 4: 4; 6.1 5: 5
Korrigera och ändra i register | 6 | Elof Paulsson | Done | 15 | 21.7 1: 15; 13.9 2: 4; 6.1 3: 0
Medlemsinformation | 7 | Elof Paulsson | Done | 10 | 21.7 1: 10; 13.9 2: 7; 6.1 3: 2; 6.1 4: 2
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
3
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 24 | 24 | 9 | 2 | 2
Task rows | 2 | Done days | 4 |  | 24 | 19.2 | 14.4 | 9.6 | 4.8
Warning! These are necessary |  | Trend |  |  | 20.2 | 12.9 | 5.6
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 20.2 1: 1; 12.9 2: 2; 5.6 3: 3; 5.6 4: 4; 5.6 5: 5
Spara informationen. | 5 | Elof Paulsson | Ongoing | 14 | 20.2 1: 14; 12.9 2: 2; 5.6 3: 0; 5.6 4: 0; 5.6 5: 0
Avslutande Css och stilning | 6 | Elof Paulsson | Done | 10 | 20.2 1: 10; 12.9 2: 7; 5.6 3: 2; 5.6 4: 2; 5.6 5: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint Sheet Template (hidden)
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips (hidden)
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
Responsible Person: Elof Paulsson
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: Elof Paulsson
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: Elof Paulsson
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person:
Initial Estimate | 9 | Work Done |  | Work Left